## Sheet1
Date | Activities | Milestone
Start-up Week (April, 6-12) | Team Formation & Project Planning | Project Plan & Work Flow Chart
1st Week (April, 13-19) | Research, Data Cleaning/Calculation, & Load to Database | Data Cleaning Files & Database
2nd Week (April, 20-26) | Data Analysis & Web Design | Website & Dynamic Charts & Map Files
3nd Week (April 27 - May 3) | Data Analysis & Prediction with Machine Learning | Web Files with Demo
4nd Week (May, 4-9) | Presentation & Practice | Project Plan Result & PP Slide??